## Week 1
Programming for Data Analysis Project
To be completed by: |  | Eamonn O Farrell
Deadline: |  | 2018-11-24
Project Week 1
% done | Phase | Due By | Notes
100% | Planning - create excel project plan | 2018-11-22 | Decided to use Project template from excel, very easy to use and update.
100% | Preparation - research possible data sets for use in project. Min 4 cols and 100 rows. | 2018-11-23 | Investigated housing price increace since crash, drink driving statistics from UK, GAA match statistics - winning margins.
100% | Create Git Hub repository for Project | 2018-11-22 | https://github.com/eamonnofarrell/Programming_Project
100% | Create Ipynb notebook for project | 2018-11-23 | Prog_Project.ipynb
0%
0%
0%
0%
0%

## Week 2
Programming for Data Analysis Project
To be completed by: |  | Eamonn O Farrell
Deadline: |  | 2018-12-01
Project Week 2
% done | Phase | Due By | Notes
100% | Planning | 2018-11-28 | decided to go with call center vice traffic metrics as subject for simulation of real world phenomenon
100% | Preparation - research of call center metrics and kpi's | 2018-11-29 | Good call center references at the International finance corporation site https://www.ifc.org/ wps/wcm/connect /75ce96004cf85d4f8752c7f81ee631cc/Tool+9.4.+Measuring+Call+Center+Performance.pdf?MOD=AJPERES
100% | Assess suitability of Numpy random package for simulation of call center voice call traffic | 2018-11-30 | Decided on poisson distribution as research shows how well it can simulate arrival of customer business at a facility
100% | load dataframe with dates as index and voice call volumes as 1st column | 2018-11-30 | Load dataframe Calls column with a poisson mean value of 3617 over a period of 12 years starting 2019
100% | Metric - average speed of ans | 2018-12-07 | researched global metrics. Decided on np.random.randint package to simulate volumes.
100% | Metric - Abandoned calls | 2018-12-07 | research benchmark fig. simulate data with poisson distribution. Set mean value to 250 for required results.
100% | Metric - abandonment rate | 2018-12-07 | % callers who hang up before reaching an agent. Global metric = 5-8%
100% | Hand-off
100% | Follow-up

## Week 3
Programming for Data Analysis Project
To be completed by: |  | Eamonn O Farrell
Deadline: |  | 2018-12-08
Project Week 3
% done | Phase | Due By | Notes
100% | Assess SLA measurement and graphing values | 2018-12-13 | slected sla level per metric and applied sla to neighbouring column for ease of reporting.
100% | Net promoter score | 2018-12-13 | research NPS - promoters, detractors. Establish benchmank - 32 for contact cent
100% | visualisation of SLA performance | 2018-12-13 | horizontal bar chart showing pass/fail.
0% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up

## Week 4
Programming for Data Analysis Project
To be completed by: |  | Eamonn O Farrell
Deadline: |  | 2018-12-14
Project Week 4
% done | Phase | Due By | Notes
0% | Planning
0% | Preparation
0% | Task a
0% | Task b
0% | Task c
0% | Task d
0% | Paperwork
0% | Hand-off
0% | Follow-up